## BD& OWNER Sign
Date
File No.
Villa for Mr.
Contractor:
Consultant
S. NO. | Description of Stage | per. Of stage | A.NO. | Description of ActivitY | per. Of Activity |  | Actual % done | Notes
[5 empty] | G.F&S.B | F.F
1 | Mobilisation | 1% | 1 | Mob.,Site office& Services. | 1% | _
2 | Excavation & Back filling | 1.5% | 2.1 | Excavation | 0.5% | _
|  |  | 2.2 | Back filling | 1% | _ |  |  | 70000 | 2000000 | 3.5
3 | Sub-structure | 9.25% | 3.1 | P.C.C. | 0.75% | _
|  |  | 3.2 | R.C.C. | 5.5% | _
|  |  | 3.3 | N. COLUMN | 0.5% | _
|  |  | 3.4 | TIE. BEAM | 1.5% | _
|  |  | 3.5 | P.C.C UNDER TILES | 1% | _ |  |  | 106.7%
4 | Super structure | 21% | 4.1 | Columns | 1.5% | 1% |  |  | 7.75
|  |  | 4.2 | Slab | 10% | 7%
|  |  | 4.3 | Parapet | 0.5% | 1%
5 | Block works | 6.25% | 5.1 | Solid block ( under Tie Beam ) | 0.75% | _
|  |  | 5.2 | H. Block | 3% | 2.5%
6 | Plaster works | 6.5% | 6.1 | Internal plaster | 2.25% | 1.25%
|  |  | 6.2 | External plaster | 1.75% | 1.25%
7 | Tiles ,Marble & Step | 9% | 7.1 | wall Tiles | 1.75% | 1.25%
|  |  | 7.2 | Floor Tiles | 2% | 1.5%
|  |  | 7.3 | Marble | 0.75% | 0.5%
|  |  | 7.4 | (Gypsum &False ) Works | 0.75% | 0.5%
8 | Water proofing Works | 3.5% | 8.1 | Footings , TB , SB.& every things UG. | 0.5% | _ |  |  | 43.75 | 0.5 | 5.5
|  |  | 8.2 | Bath Room & kitchen. | _ | 0.5%
|  |  | 8.3 | Roof works | _ | 2.5%
9 | Painting works | 7% | 9.1 | internal primer | 0.3% | 0.2%
|  |  | 9.2 | Internal putty | 1% | 0.5%
|  |  | 9.3 | Internal Top coat | 1.25% | 1%
|  |  | 9.4 | External Primer | 0.25%
|  |  | 9.5 | texture | 1%
|  |  | 9.6 | External Top coat | 1.5%
10 | Joinery & Aluminium works | 6.75% | 10.1 | Frames | 0.5% | 0.25%
|  |  | 10.2 | Doors | 1% | 0.75%
|  |  | 10.3 | Handrail ( internal ) | 0.5%
|  |  | 10.4 | Kitchen cabinets and wardrobes | 0.75%
|  |  | 10.5 | Aluminium Works | 1.75% | 1.25%
sum of page |  | 71.75% |  |  |  |  | 0
Engineer
Date
File No.
Villa for Mr.
Contractor:
Consultant
S. NO. | Description of Stage | per. Of stage | A.NO. | Description of ActivitY | per. Of Activity |  | Actual % done | Notes
[5 empty] | G.F&S.B | F.F
sum of the previous |  | 71.75% |  |  |  |  | 0
11 | Electrical . Works | 6.5% | 11.1 | Conduits in Slab | 0.2% | 0.25% | 0.2
|  |  | 11.2 | Conduits & GI Boxes in Wall & under G. | 0.15% | 0.2% | 0.15
|  |  | 11.3 | Electrical wires, TV wires & telephone wires | 0.5% | 0.5%
|  |  | 11.4 | XLPE cables, Manholes, Accessories (Lugs, Gland) | 0.5% | 0.5%
|  |  | 11.5 | DBs, MDB, Meter cabinet | 0.75% | 0.75%
|  |  | 11.6 | Wiring Accessories (Power Socket outlet, Lighting switches, isolator, Flex outlet, Spur outlet, Cooker Control Unit -CCU…etc) | 0.25% | 0.25%
|  |  | 11.7 | Light Fitting (Internal & External) | 0.25% | 0.25%
|  |  | 11.8 | DEWA CT power Meter released, testing & commissioning | 1%
|  |  | 11.9 | Earthing system (copper Rods, manholes, cables) | 0.2%
12 | HVAC Works | 5% | 12.1 | Against installation of indoor units (FCU) & Ducting | 1% | 1%
|  |  | 12.2 | Against installation of outdoor Units & Refigrant piping | 1% | 1%
|  |  | 12.3 | Against testing & commissioning | 1%
13 | Plumbing works | 6.5% | 13.1 | Water Supply Pipes ( Internal) | 0.25% | 0.2%
|  |  | 13.2 | Water Supply Pipes (external) | 0.25%
|  |  | 13.4 | Solar and Electrical Water Heater | 0.3% | 0.25%
|  |  | 13.5 | DEWA Water Meter released, testing & commissioning | 0.25%
|  |  | 13.6 | Drainage pipes ( Internal) | 0.25% | 0.25%
|  |  | 13.7 | Sanitary Wares | 0.75% | 0.5%
|  |  | 13.8 | Drainage of A/C. | 0.25%
|  |  | 13.9 | manholes ( Including Pipe +Cover) | 1.25%
|  |  | 13.1 | Water tanks & pumps | 0.75%
|  |  | 13.11 | Septic tank and soakaway or connection | 1%
sum of page |  | 89.75% |  |  |  |  | 0.35
Engineer
Date |  | 2018-02-14
File No. |  | 1015888
Villa for Mr. |  | خالد راشد خلفان بن شقوي العليلي
Contractor: |  | براون فالكون للمقاولات
Consultant |  | سكوباس للاستشارات الهندسية
S. NO. | Description of Stage | per. Of stage | A.NO. | Description of ActivitY | per. Of Activity |  | Actual % done | Notes
[5 empty] | G.F&S.B | F.F
sum of the previous |  | 89.75% |  |  |  |  | 0.35
14 | compound Wall & Gates | 7.5% | 14.1 | Excavation | 0.25% |  | 0.25
|  |  | 14.2 | P.C.C. | 0.5% |  | 0.5
|  |  | 14.3 | R.C.C. | 1% |  | 1
|  |  | 14.4 | TIE. BEAM | 0.75% |  | 0.75
|  |  | 14.5 | Solid block ( under Tie Beam ) | 0.25% |  | 0.25
|  |  | 14.6 | H. Block | 1.25% |  | 1.25
|  |  | 14.7 | Columns & Bopying Beam | 0.75% |  | 0.75
|  |  | 14.8 | Plaster | 1%
|  |  | 14.9 | Paints | 1%
|  |  | 14.1 | Gates | 0.75%
15 | External Works | 2.75% | 15.1 | Spiral Stair or Monkey Stair | 0.75%
|  |  | 15.2 | Interlock & Kerbstone | 0.75%
|  |  | 15.3 | Car parking | 0.75%
|  |  | 15.4 | Handrail ( external ) | 0.25%
|  |  | 15.5 | Site levelling,cleaning and H.Over. | 0.25%
Total |  | 100% |  |  |  |  | 5.1
Engineer
______________________________

## Compatibility Report
Compatibility Report for new Break Down & BOQ.xls
Run on 26-10-2009 10:28
The following features in this workbook are not supported by earlier versions of Excel. These features may be lost or degraded when you save this workbook in an earlier file format.
Minor loss of fidelity | # of occurrences
Some cells or styles in this workbook contain formatting that is not supported by the selected file format. These formats will be converted to the closest format available. | 36